## Renovation
QUOTATION FOR AGICO RENOVATGION PROJECT
S/No | Nature and Discription of Work | A/U | Qty (Approx) | Rate | Total | Time Scheduled |  | Remarks
[6 empty] | Date From | Date To
STAGE - 1
Dismantaling Work
1 | Dismantling/Removal of existing of POP Ceiling, Lights, Wooden Cabnits, 2 x Executive Cabins, Office Furniture, Electric/Telephone/ Networking wirings. | Job | Lumsum
2 | Dispose off useless materials / debries out side the muncipal limit | Job | Lumsum
STAGE - 2
Tiles Work
1 | Provision and Laying 1" to 2" thick kacha PCC Plaster of 1 : 4 Cement Sand Mortar base for Tiles | Sqft | 4500
2 | Porvision and fixing of 24" x 24" RAK Tiles (Design Code. 9GPD1 as per available sample) with Tile Bond (Shabbir) and matching filling grout (Shabbir) | Sft | 4500
3 | Provision and Fixing of 4" Tiles Skirting as above Tiles | Rft | 190
STAGE - 3
Executive Cabins
Provision and making of 3 x Executive Cabin Size 11' x 9'x 8' with following details:- Wood Work: Full Height (7') partition 1'.5" x 2" Partal wood framing and 10mm thick MDF Lasani Board (Malaysia) on both sides and 12mm glass partition
Glass Work
1 | Glass partition 12mm/Aluminium 2mm D48. Size 9 x 6 x 6'.5" | Sft | 315
2 | Glass Door 12mm Size 6'.5" x 3' with Motor (New Star Japan), Handle, etc. | Sft | 20
3 | Fixing of Frosted Paper | Sft | 100
4 | Fixing of Ante Shetter Paper | Sft | 165
Cabnits
1 | Re-Fixing of full height Wooden Cabnit Size 15' x 8' x 16" |  | 120
2 | Provision and making full height wooden Cabnits Size 45' x 8' x 16" with shelf as per exisiting sample. | Sft | 360
3 | Polishing Old Wooden Cabnits if required | Job | Lumsum
Work Stations
1 | Provision and making Work Station 5' x 5' with single mobile drawer unit (2 drawers + door box) Key Board Tray consisting of lamination board top and partition of partal wood frame 2.5" x 1.5" and 1/2" lasani board and 1/8" Beach Ply as per existing sample. | No | 18
2 | Provision and making Work Station 4' x 4' with single mobile drawer unit (2 drawers + door box) Key Board Tray consisting of lamination board top and partition of partal wood frame 2.5" x 1.5" and 1/2" lasani board and 1/8" Beach Ply as per existing sample. | No | 4
3 | Provision and making Work Station 4' x 2' with single mobile drawer unit (2 drawers + door box) Key Board Tray consisting of lamination board top and partition of partal wood frame 2.5" x 1.5" and 1/2" lasani board and 1/8" Beach Ply as per existing sample. | No | 4
4 | Provision and making Work Station 5' x 2' with single mobile drawer unit (2 drawers + door box) Key Board Tray consisting of lamination board top and partition of partal wood frame 2.5" x 1.5" and 1/2" lasani board and 1/8" Beach Ply as per existing sample. | No | 2
Battery Room
1 | Provision and Fixing of full height 1/2" Cement Board Partition using 2.5" x 1.5" partal wood frame . | Sft | 90
2 | Shifting of 12mm Glass door Size 6'.5" x 3' including cutting and polishing work | Sft | 20
STAGE - 4
Electric Work
1 | Provision and installation of Wiring 7/29 (Pak Cable) in 20mm dia PVC Pipe from distribution board to switch boxes. | Point | 15
2 | Provision and Fixing of 5 Gang Switch (Clipsal). | Point | 10
3 | Provision and Fixing of Multi Socket (Schneider) with back box. | Point | 70
4 | Provision and Fixing of 2' x 2' LED 40 watt Panel Lights (Philps). | No | 45
5 | Provision and installation of Wiring 3/29 (Pak Cable) in 20mm dia PVC Pipe for Ligths Point to Point. | Point | 45
6 | Provision and Fixing of Telephone Wiring / Socket outlid (Clipsal) with Cat. 5 Cable in PVC Pipe. | Point | 35
Ceiling Work
1 | Provision and Fixing 600 x 600mm single side laminated Gypsum board false ceiling (DFB) with aluminium foil at back side with imported aluminium powder quoted suspension system (SKM UT/FUT series)with Disco T as per existing sample. | Sft | 4500
Terms and Conditions
1 | Description of works will include all other necessory details involved in the work.
2 | Quoted prices will be inclusive of taxes.
3 | Contracter will give time schedule for all stages of work within his quotation.
4 | Part payment will be made on completion of each stage of work.
Delay in work
1 | In the event of delay in work the contractor shall inform the company before expiry of time schedule giving reasons with justification for it. The company shall have the right to take following action:- a. Cancel the work order and / or. b. Get the work completed from elsewhere at the risk and expense of the contractor and without notice to him, or. c. Recover liquilated damages when the company is satisified the the falaure to complete the work in schedule time has been for reasons within the control of the contractor and / or if the company has suffered loss for reasons of delay in completion of work. d. Liquidated damages if imposed will be recovered at the rate of Rs. 5,000/- per day or part of a day.
e. Design and quality of all works materials will be subject to satisfaction and prior approval of the company Engineer.
f. Contractor will deposit security amount of Rs. 100,000/- (One hundred thousand) in the shape of Bank Draft/Pay order in name of Askari General Insurance Co. Ltd. Rawalpindi before receipt of Work Order
g. Existing/re-use material price will be balanced in the invoices.
e. Renovation will commence from 3rd Februry 2018.